## Sheet1
Not Started | Work Plan - Priyanka | ETA(in hours) | STATUS(with Time logged) | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
In Progress | Populate the Training Partner name on the TP table ¦ 2 hrs | 2
In QA | Selection Committee date should not get populated as null ¦ 1.5 hrs | 1.5 | 1.5
Done | Type of file while browsing for image should be jpeg, png not all files ¦ 0.75 hrs | 0.75
| Cells are not blocked ¦ Excel sheet in Generated Batch Id ¦ 2.25 hrs | 2.25
| Complete Name of Job role not populated in generated Batch Id excel Sheet ¦ 1.5 hrs | 1.5
| Submit User Input Data ¦ Master Sheet Import ¦ 3 hrs | 3 | 4
| Excel sheet Should have batchId in its name ¦ Generate batch ¦ 1.5 hrs | 1.5
| In Generate Batch report, user should be able to choose two images on one browse ¦ 1.5 hrs | 1.5
| Disable browse button when Batch Id & Scgj Batch number not selected ¦ 0.75 hrs | 0.75
| On browse, selected image name should be visible in text field ¦ 0.75 hrs | 0.75
| Batch Report Generation ¦ 7.5 hrs | 7.5
| Download Zip not working for some batchId ¦ 3 hrs | 3
| Integration Testing ¦ 3hrs | 3
|  | 29 | 5.5
Work Plan - Pooja
| Creation of Dump Data ¦ 2 hrs | 2
| Frontend cosmetic fixes ¦ Generate Credentials ¦ 2 hr. 30 min | 2.5 | 2.75
| Frontend validation ¦ View documents ¦ 45 min | 0.75
| SCGJ batch number field alignment ¦ Generate batch report ¦ 45 min | 0.75
| No guidelines in Upload documents ¦ 3 hr. | 3
| NSDC registration number check ¦ 1 hr. 30 min | 1.5 | 3
| No validation when there is no data regarding batch id ¦ Upload documents ¦ 45 Min | 0.75
| Updated Targets ¦ frontend ¦ 1.5 hrs | 1.5
| Recent generated batch not populating in dropdown ¦ Master sheets import ¦ 45 min | 0.75
| Candidates trained ¦ dashboard ¦ 4 hr. 30 min | 4.5
| Generated report not populating in single click ¦ Generate Report ¦ 1 hr. 30 min | 1.5 |  | 2+F1:O266 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
| Favicon ¦ SCGJ logo ¦ 45 min | 0.75
|  | 20.25 | 5.75
Work Plan - Prateek
| Upload Documents - Training Partner ¦ 7.5 Hrs | 7.5
| Handover the Project to SCGJ ¦ 6 hrs | 6
| Update Targets Functionality - Admin ¦ Back end ¦ 2.5hr | 2.5
| Data Import ¦ Training Partner ¦ 15 hr | 15
| Search Functionality ¦ View Documents ¦ 3hr | 3
| Acceptance Criteria ¦ NSKFDC - App ¦ 2 hrs | 2
| PFP Discussion ¦ Revenue Model ¦ Training Identification ¦ 1 hr | 1
| Training Partner Dashboard ¦ Targets ¦ 1 hr | 1
| Upload Functionality ¦ Data Import ¦ 2 hr | 2
40