## Sheet1
Work Plan - Priyanka | ETA(in hours) | STATUS(with Time logged)
Populate the Training Partner name on the TP table ¦ 2 hrs | 2
Selection Committee date should not get populated as null ¦ 1.5 hrs | 1.5
Type of file while browsing for image should be jpeg, png not all files ¦ 0.75 hrs | 0.75
Cells are not blocked ¦ Excel sheet in Generated Batch Id ¦ 2.25 hrs | 2.25
Complete Name of Job role not populated in generated Batch Id excel Sheet ¦ 1.5 hrs | 1.5
Submit User Input Data ¦ Master Sheet Import ¦ 3 hrs | 3 | 4
Excel sheet Should have batchId in its name ¦ Generate batch ¦ 1.5 hrs | 1.5
In Generate Batch report, user should be able to choose two images on one browse ¦ 1.5 hrs | 1.5
Disable browse button when Batch Id & Scgj Batch number not selected ¦ 0.75 hrs | 0.75
On browse, selected image name should be visible in text field ¦ 0.75 hrs | 0.75
Batch Report Generation ¦ 7.5 hrs | 7.5
Download Zip not working for some batchId ¦ 3 hrs | 3
Integration Testing ¦ 3hrs | 3
| 29 | 4
Work Plan - Pooja
Creation of Dump Data ¦ 2 hrs | 2
Frontend cosmetic fixes ¦ Generate Credentials ¦ 2 hr. 30 min | 2.5 | 2.75
Frontend validation ¦ View documents ¦ 45 min | 0.75
SCGJ batch number field alignment ¦ Generate batch report ¦ 45 min | 0.75 |  | Not Started
No guidelines in Upload documents ¦ 3 hr. | 3 |  | In Progress
NSDC registration number check ¦ 1 hr. 30 min | 1.5 |  | In QA
No validation when there is no data regarding batch id ¦ Upload documents ¦ 45 Min | 0.75 |  | Done
Updated Targets ¦ frontend ¦ 1.5 hrs | 1.5
Recent generated batch not populating in dropdown ¦ Master sheets import ¦ 45 min | 0.75
Candidates trained ¦ dashboard ¦ 4 hr. 30 min | 4.5
Generated report not populating in single click ¦ Generate Report ¦ 1 hr. 30 min | 1.5
Favicon ¦ SCGJ logo ¦ 45 min | 0.75
20.25
Work Plan - Prateek
Upload Documents - Training Partner ¦ 7.5 Hrs | 7.5
Handover the Project to SCGJ ¦ 6 hrs | 6
Update Targets Functionality - Admin ¦ Back end ¦ 2.5hr | 2.5
Data Import ¦ Training Partner ¦ 15 hr | 15
Search Functionality ¦ View Documents ¦ 3hr | 3
Acceptance Criteria ¦ NSKFDC - App ¦ 2 hrs | 2
PFP Discussion ¦ Revenue Model ¦ Training Identification ¦ 1 hr | 1
Training Partner Dashboard ¦ Targets ¦ 1 hr | 1
Upload Functionality ¦ Data Import ¦ 2 hr | 2
40